## pmr
ANNEX B
Philippine Center for Postharvest Development and Mechanization Procurement Monitoring Report as of June 30, 2022
Code (UACS/PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
PHilMech-RCEF-21-09-22 | Supply, Delivery, Installation, Testing and Commissioning of Various Rice Mills | [17 empty] | 358774500 |  | 358774500 | 231364000 |  | 245636000 | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 9 units Single-Pass Rice Mill (Mobile/Trailed Type) for Luzon A (Region I) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | 1st Failure of Bidding (Resolution No. 22-02-14) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 8032500 |  | 8032500 | 1st Failure of Bidding (Resolution No. 22-02-14) |  | 8028000
| Supply, Delivery, Installation, Testing and Commissioning of 7 units Single-Pass Rice Mill (Mobile/Trailed Type) for Luzon B (Regions CAR & II) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | 1st Failure of Bidding (Resolution No. 22-02-14) | N/A | N/A | N/A | N/A | N/A |  | 6247500 |  | 6247500 | 1st Failure of Bidding (Resolution No. 22-02-14) |  | 6244000
| Supply, Delivery, Installation, Testing and Commissioning of 4 units Single-Pass Rice Mill (Mobile/Trailed Type) for Region 2 - Island Municipality of Isabela (Maconacon and Palanan) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-10-54) | N/A | N/A | N/A | N/A | N/A |  | 3780000 |  | 3780000 | 1st Failure of Bidding (Resolution No. 21-10-54) |  | 1st Failure of Bidding (Resolution No. 21-10-54)
| Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Luzon A (Regions I & III) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 4389000 |  | 4389000
| Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Luzon C (Regions IV-A & V) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 4389000 |  | 4389000
| Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Region VI | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 4389000 |  | 4389000
| Supply, Delivery, Installation, Testing and Commissioning of 3 units Single Pass Rice Mill (Stationary) for Region VIII | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 3291750 |  | 3291750
| Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Mindanao A (Regions IX, X & CARAGA) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 4389000 |  | 4389000
| Supply, Delivery, Installation, Testing and Commissioning of 3 units Single Pass Rice Mill (Stationary) for Mindanao B (Regions XI & XII) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 3291750 |  | 3291750
| Supply, Delivery, Installation, Testing and Commissioning of 6 units Multi Stage Rice Mill for Region I | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | Declared Failed Bidding by the HOPE | N/A | N/A | N/A | N/A | N/A |  | 28350000 |  | 28350000 | 28320000 |  | 28320000
| Supply, Delivery, Installation, Testing and Commissioning of 5 units Multi Stage Rice Mill for Region II | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | Declared Failed Bidding by the HOPE | N/A | N/A | N/A | N/A | N/A |  | 23625000 |  | 23625000 | 23620000 |  | 23620000
| Supply, Delivery, Installation, Testing and Commissioning of 5 units Multi Stage Rice Mill for Region III | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | Declared Failed Bidding by the HOPE | N/A | N/A | N/A | N/A | N/A |  | 23625000 |  | 23625000 | 23600000 |  | 23600000
| Supply, Delivery, Installation, Testing and Commissioning of 16 units Multi Stage Rice Mill for Region IV-B | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | 1st Failure of Bidding (Resolution No. 22-02-08) | N/A | N/A | N/A | N/A | N/A |  | 75600000 |  | 75600000 | 75584000 |  | 75584000
| Supply, Delivery, Installation, Testing and Commissioning of 6 units Multi Stage Rice Mill for Regions IV-A & V | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | Declared Failed Bidding by the HOPE | N/A | N/A | N/A | N/A | N/A |  | 28350000 |  | 28350000 | 28320000 |  | 28320000
| Supply, Delivery, Installation, Testing and Commissioning of 7 units Multi Stage Rice Mill for Antique, Capiz and Iloilo | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | Declared Failed Bidding by the HOPE | N/A | N/A | N/A | N/A | N/A |  | 33075000 |  | 33075000 | 33040000 |  | 33040000
| Supply, Delivery, Installation, Testing and Commissioning of 4 units Multi Stage Rice Mill for Negros Occidental | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | October 23-October 29, 2021 | October 30 - December 13, 2021 | Declared Failed Bidding by the HOPE | N/A | N/A | N/A | N/A | N/A |  | 18900000 |  | 18900000 | 18880000 |  | 18880000
| Supply, Delivery, Installation, Testing and Commissioning of 8 units Multi Stage Rice Mill for Regions VII & VIII | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-10-54) | N/A | N/A | N/A | N/A | N/A |  | 37800000 |  | 37800000 | 1st Failure of Bidding (Resolution No. 21-10-54) |  | 1st Failure of Bidding (Resolution No. 21-10-54)
| Supply, Delivery, Installation, Testing and Commissioning of 5 units Multi Stage Rice Mill for Mindanao A (Regions IX, X & CARAGA) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 23625000 |  | 23625000
| Supply, Delivery, Installation, Testing and Commissioning of 5 units Multi Stage Rice Mill for Mindanao B (Regions XI & XII) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-09-30 | 2021-10-08 | 2021-10-22 | 2021-10-22 | [9 empty] | 23625000 |  | 23625000
PHilMech-RCEF-21-09-25 | Supply, Delivery and Testing of De-Stoners | [17 empty] | 5699400 |  | 5699400 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-11 | N/A
| Supply, Delivery, Installation and Testing of 14 units De-Stoner for Luzon (Regions CAR, I & II) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-09 | 2021-11-17 |  | 2021-12-02 | December 2-8, 2021 | December 9-20, 2021 | 1st Failure of Bidding (Resolution No. 12-12-72) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 1734600 |  | 1734600 | 1st Failure of Bidding (Resolution No. 12-12-72) |  | 1st Failure of Bidding (Resolution No. 12-12-72)
| Supply, Delivery, Installation and Testing of 21 units De-Stoner for Visayas (Regions VI,VII & VIII) | [17 empty] | 2601900 |  | 2601900
| Supply, Delivery, Installation and Testing of 11 units De-Stoner for Luzon (Regions X & XII) | [17 empty] | 1362900 |  | 1362900
PHilMech-RCEF-21-07-16 | Rebidding for the Supply, Delivery and Testing of Rice Precision Seeders | [23 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | N/A
| Rebidding for the Supply, Delivery and Testing of 10 Units Rice Precision Seeders for Visayas (Regions VI, VII & VIII) | FMFOD | NO | Competitive Bidding | N/A | 2021-07-22 | 2021-07-30 | 2021-09-08 | 2021-09-08 | September 9-15, 2021 | September 16- October 29, 2021 | 2021-12-16 | 2021-12-17 | 12/27/2022 | 2022-06-09 | on-going | on-going | Special Purpose Fund | 16780000 |  | 16780000 | 16779500 |  | 16779500
PHilMech-RCEF-21-09-20 | Rebidding for the Supply and Delivery and Testing of Walking-Type Agricultural Tractors | [17 empty] | 125124720 |  | 125124720 | 96568150 |  | 96568150 | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-09-15 | N/A
| Rebidding for the Supply and Delivery and Testing of 147 units Walking-Type Agricultural Tractors with Complete Accessories for Regions CAR, I & II | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | October 22-October 28, 2021 | October 29 - December 12, 2021 | 2022-01-03 | 2022-01-04 | 2022-01-07 | 2022-06-09 | on-going | on-going | Special Purpose Fund | 24109470 |  | 24109470 | 24034500 |  | 24034500
| Rebidding for the Supply and Delivery and Testing of 138 units Walking-Type Agricultural Tractors with Complete Accessories for Regions III, IVA & V | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | October 22-October 28, 2021 | October 29 - December 12, 2021 | 2nd Failure of Bidding per BAC Reso No. 22-03-17 | N/A | N/A | N/A | N/A | N/A |  | 22633380 |  | 22633380 | 2nd Failure of Bidding per BAC Reso No. 22-03-17
| Rebidding for the Supply and Delivery and Testing of 135 units Walking-Type Agricultural Tractors with Complete Accessories for Regions IX, X, XI, XII, CARAGA & BARMM | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | October 22-October 28, 2021 | October 29 - December 12, 2021 | 2022-01-03 | 2022-01-04 | 2022-01-14 | 2022-06-09 | on-going | on-going |  | 22141350 |  | 22141350 | 22072500 |  | 22072500
| Rebidding for the Supply and Delivery and Testing of 12 units Walking-Type Agricultural Tractors with Complete Accessories (For Island Provinces) for Region II | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | N/A | N/A | 2nd Failure of Bidding per BAC Reso No. 21-10-51 | N/A | N/A | N/A | N/A | N/A |  | 2057580 |  | 2057580 | 2nd Failure of Bidding per BAC Reso No. 21-10-51
| Rebidding for the Supply and Delivery and Testing of 21 units Walking-Type Agricultural Tractors with Complete Accessories (For Island Provinces) for Regions IV-B & V | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | October 22-October 28, 2021 | October 29 - December 12, 2021 | 2nd Failure of Bidding per BAC Reso No. 22-03-17 | N/A | N/A | N/A | N/A | N/A |  | 3600765 |  | 3600765 | 2nd Failure of Bidding per BAC Reso No. 22-03-17
| Rebidding for the Supply and Delivery and Testing of 167 units Walking-Type Agricultural Tractors with Complete Accessories (For Island Provinces) for Regions VI & VII | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | October 22-October 28, 2021 | October 29 - December 12, 2021 | 2022-01-03 | 2022-01-04 | 2022-01-14 | 2022-06-09 | on-going | on-going |  | 28634655 |  | 28634655 | 28598750 |  | 28598750
| Rebidding for the Supply and Delivery and Testing of 128 units Walking-Type Agricultural Tractors with Complete Accessories (For Island Provinces) for Region VIII | FMFOD | NO | Competitive Bidding | N/A | 2021-09-12 | 2021-09-20 | Oct. 4 & 21, 2021 | Oct. 4 & 21, 2021 | October 22-October 28, 2021 | October 29 - December 12, 2021 | 2022-01-03 | 2022-01-04 | 2022-01-14 | 2022-06-09 | on-going | on-going |  | 21947520 |  | 21947520 | 21862400 |  | 21862400
PHilMech-RCEF-21-10-27 | Supply, Delivery, Installation, Testing and Commissioning of Various Heated Air Mechanical Dryers | [17 empty] | 837700000 |  | 837700000 | 1st Failure of Bidding (Resolution No. 21-12-62) |  | 1st Failure of Bidding (Resolution No. 21-12-62) | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | Nov. 10 & 11, 2021 | Nov. 10 & 11, 2021 | Nov. 10 & 11, 2021 | Nov. 10 & 11, 2021 | Nov. 10 & 11, 2021
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region I | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 13 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region II | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 33800000 |  | 33800000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region III | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 5 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region IV-A | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 13000000 |  | 13000000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Oriental Mindoro- District I (Municipality/City of Calapan, Naujan and Victoria) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Oriental Mindoro- District I (Municipality/City of Baco, Pola and San Teodoro) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 14 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Oriental Mindoro (District 2) | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 36400000 |  | 36400000
| Supply, Delivery, Installation, Testing, and Commissioning of 2 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Palawan | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 5200000 |  | 5200000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region V | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 26000000 |  | 26000000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Capiz & Negros Occidental | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Iloilo | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 26000000 |  | 26000000
| Supply, Delivery, Installation, Testing, and Commissioning of 3 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region VIII | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 7800000 |  | 7800000
| Supply, Delivery, Installation, Testing, and Commissioning of 11 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region IX | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 28600000 |  | 28600000
| Supply, Delivery, Installation, Testing, and Commissioning of 6 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region X | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 15600000 |  | 15600000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Regions XI & XII | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 7 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Agusan del Norte & Agusan del Sur | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 18200000 |  | 18200000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Surigao del Sur | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 20800000 |  | 20800000
| Supply, Delivery, Installation, Testing, and Commissioning of 7 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for CAR & Cagayan | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 14700000 |  | 14700000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Isabela, Quirino & NV | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 21000000 |  | 21000000
| Supply, Delivery, Installation, Testing, and Commissioning of 12 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Pangasinan | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 25200000 |  | 25200000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Ilocos Sur, Ilocos Norte & La Union | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 16800000 |  | 16800000
| Supply, Delivery, Installation, Testing, and Commissioning of 12 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Bulacan | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 25200000 |  | 25200000
| Supply, Delivery, Installation, Testing, and Commissioning of 9 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Nueva Ecija | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 18900000 |  | 18900000
| Supply, Delivery, Installation, Testing, and Commissioning of 11 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Pampanga & Tarlac | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 23100000 |  | 23100000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Regions IVA & V | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 16800000 |  | 16800000
| Supply, Delivery, Installation, Testing, and Commissioning of 13 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region IVB | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 27300000 |  | 27300000
| Supply, Delivery, Installation, Testing, and Commissioning of 4 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region VI | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 8400000 |  | 8400000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region VII | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 21000000 |  | 21000000
| Supply, Delivery, Installation, Testing, and Commissioning of 15 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Leyte District 1 | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 31500000 |  | 31500000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Leyte District 2, 4 & 5 | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 16800000 |  | 16800000
| Supply, Delivery, Installation, Testing, and Commissioning of 9 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Regions IX,X & CARAGA | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 18900000 |  | 18900000
| Supply, Delivery, Installation, Testing, and Commissioning of 9 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region XI | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 18900000 |  | 18900000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Regions XII & BARMM | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 21000000 |  | 21000000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region II | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 19200000 |  | 19200000
| Supply, Delivery, Installation, Testing, and Commissioning of 7 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Regions III & IVA | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 16800000 |  | 16800000
| Supply, Delivery, Installation, Testing, and Commissioning of 13 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region IVB | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 31200000 |  | 31200000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region VI | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 24000000 |  | 24000000
| Supply, Delivery, Installation, Testing, and Commissioning of 7 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region VII | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 16800000 |  | 16800000
| Supply, Delivery, Installation, Testing, and Commissioning of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Leyte District 1, 2 & 3 | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 19200000 |  | 19200000
| Supply, Delivery, Installation, Testing, and Commissioning of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Leyte District 4 & 5 | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 24000000 |  | 24000000
| Supply, Delivery, Installation, Testing, and Commissioning of 2 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Southern Leyte | FMFOD | NO | Competitive Bidding | 2021-09-17 | 2021-11-08 | 2021-11-16 | 2021-12-07 | 2021-12-07 | N/A | N/A | 1st Failure of Bidding (Resolution No. 21-12-62) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 4800000 |  | 4800000
PHilMech-RCEF-21-11-28 | Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of Various Rice Mills | [17 empty] | 118997846 |  | 118997846 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 4 units Single-Pass Rice Mill (Mobile/Trailed Type) for Region 2 - Island Municipality of Isabela (Maconacon and Palanan) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | N/A | N/A | 2nd Failure of Bidding (Resolution No. 22-01-04) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 4628700 |  | 4628700
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Luzon A (Regions I & III) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2022-03-28 | 2022-06-09 | 2022-06-13 | 2022-06-15 | on-going | on-going | Special Purpose Fund | 4557572 |  | 4557572 | 4556000 |  | 4556000
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Luzon C (Regions IV-A & V) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2022-03-28 | 2022-06-09 | 2022-06-13 | 2022-06-15 | on-going | on-going | Special Purpose Fund | 4557572 |  | 4557572 | 4556000 |  | 4556000
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Region VI | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2022-03-28 | 2022-06-09 | 2022-06-15 | 2022-06-16 | on-going | on-going | Special Purpose Fund | 4557572 |  | 4557572 | 4551200 |  | 4551200
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 3 units Single Pass Rice Mill (Stationary) for Region VIII | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2022-03-28 | 2022-06-09 | 2022-06-13 | 2022-06-15 | on-going | on-going | Special Purpose Fund | 3418179 |  | 3418179 | 3417000 |  | 3417000
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 4 units Single Pass Rice Mill (Stationary) for Mindanao A (Regions IX, X & CARAGA) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2022-03-28 | 2022-06-09 | 2022-06-13 | 2022-06-15 | on-going | on-going | Special Purpose Fund | 4557572 |  | 4557572 | 4556000 |  | 4556000
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 3 units Single Pass Rice Mill (Stationary) for Mindanao B (Regions XI & XII) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2022-03-28 | 2022-06-09 | 2022-06-13 | 2022-06-15 | on-going | on-going | Special Purpose Fund | 3418179 | 25066646 | 3418179 | 3417000 | 25053200 | 3417000
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 8 units Multi Stage Rice Mill for Regions VII & VIII | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 1/21-26/20222 | 2022-03-13 | 2nd Failure of Bidding (Resolution No. 22-03-24) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 39690000 |  | 39690000
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 5 units Multi Stage Rice Mill for Mindanao A (Regions IX, X & CARAGA) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | N/A | N/A | 2nd Failure of Bidding (Resolution No. 22-01-04) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 24806250 |  | 24806250
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of 5 units Multi Stage Rice Mill for Mindanao B (Regions XI & XII) | FMFOD | NO | Competitive Bidding | N/A | 2021-12-07 | 2021-12-14 | 2022-01-21 | 2022-01-21 | N/A | N/A | 2nd Failure of Bidding (Resolution No. 22-01-04) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 24806250 |  | 24806250
PHilMech-RCEF-21-11-29 | Supply, Delivery, Installation, Testing and Commissioning of Multi-Stage Rice Mills | [17 empty] | 194400000 |  | 194400000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07
| Supply, Delivery, Installation, Testing and Commissioning of 1 unit Multi-Stage Rice Mill for Region II | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-06 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 2022-01-21 | N/A | 1st Failure of Bidding (Resolution No. 22-02-12) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 48600000 |  | 48600000 | N/A |  | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 1 unit Multi-Stage Rice Mill for Region V | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-06 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 2022-01-21 | N/A | 1st Failure of Bidding (Resolution No. 22-02-12) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 48600000 |  | 48600000 | N/A |  | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 1 unit Multi-Stage Rice Mill for Region VII | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-06 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 2022-01-21 | N/A | 1st Failure of Bidding (Resolution No. 22-02-12) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 48600000 |  | 48600000 | N/A |  | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 1 unit Multi-Stage Rice Mill for Region X | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-06 | 2021-12-14 | 2022-01-21 | 2022-01-21 | 2022-01-21 | N/A | 1st Failure of Bidding (Resolution No. 22-02-12) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 48600000 |  | 48600000 | N/A |  | N/A
PHilMech-RCEF-21-11-30 | Supply, Delivery, Installation, Testing And Commissioning of Heated Air Mechanical Grain Dryers- Recirculating Batch Type | [17 empty] | 23200000 |  | 23200000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07
| Supply, Delivery, Installation, Testing and Commissioning of 2 units Heated Air Mechanical Grain Dryers- Recirculating Batch Type for Region II | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-07 | 2021-12-15 | 2022-01-20 | 2022-01-20 | N/A | N/A | 1st Failure of Bidding (Resolution No. 22-01-05) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 5800000 |  | 5800000 | N/A |  | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 2 units Heated Air Mechanical Grain Dryers- Recirculating Batch Type for Region V | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-07 | 2021-12-15 | 2022-01-20 | 2022-01-20 | N/A | N/A | 1st Failure of Bidding (Resolution No. 22-01-05) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 5800000 |  | 5800000 | N/A |  | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 2 units Heated Air Mechanical Grain Dryers- Recirculating Batch Type for Region VII | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-07 | 2021-12-15 | 2022-01-20 | 2022-01-20 | N/A | N/A | 1st Failure of Bidding (Resolution No. 22-01-05) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 5800000 |  | 5800000 | N/A |  | N/A
| Supply, Delivery, Installation, Testing and Commissioning of 2 units Heated Air Mechanical Grain Dryers- Recirculating Batch Type for Region X | FMFOD | NO | Competitive Bidding | 2021-11-23 | 2021-12-07 | 2021-12-15 | 2022-01-20 | 2022-01-20 | N/A | N/A | 1st Failure of Bidding (Resolution No. 22-01-05) | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 5800000 |  | 5800000 | N/A |  | N/A
| SUPPLY, DELIVERY AND TESTING OF WALKING-TYPE AGRICULTURAL TRACTORS FOR MINDANAO | [17 empty] | 32509360
RFQ R-21-01-11 | 121 Units Walking-Type Agricultural Tractors for Mindanao (Regions IX, X, XI, XII & CARAGA) | FMFOD | NO | NP-53.1 Two Failed Biddings | N/A | 01/30/2021 | N/A | 2021-02-08 | 2021-02-08 | February 9-15, 2021 | 4/1/2021 | 4/20/2021 | 04/27/2021 | 2021-06-14 | 2022-06-21 | 2022-02-14 | 2022-06-13 | Special Purpose Fund | 17182000 |  | 17182000 | 16819000 |  | 16819000 | N/A | N/A | N/A | N/A | N/A | N/A
RFQ R- 21-03-236 | 108 Units Walking-Type Agricultural Tractors for Mindanao (Regions IX, X, XI, XII & CARAGA” | FMFOD | NO | NP-53.1 Two Failed Biddings | N/A | 03/26/2021 | N/A | 2021-04-08 | 2021-04-08 | April 9-15, 2021 | 05/10/2021 | 05/21/2021 | 05/24/2021 | 2021-06-14 | 2021-06-21 | 2022-02-14 | 2022-06-13 | Special Purpose Fund | 15327360 |  | 15327360 | 15336000 |  | 15336000 | N/A | N/A | N/A | N/A | N/A | N/A
PHilMech-Goods-21-10-14 | Supply of Labor and Materials for the Fabrication, Delivery, Installation, and Testing of Research Prototype of Fluidized Bed Drying System and Greenhouse Type | [17 empty] | 9155290.9 | [5 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2021-11-08
| Supply of Labor and Materials for the Fabrication, Delivery, Installation, and Testing of 2 units Research Prototype of Greenhouse Type Solar Dryer in Quezon Province | AMD | NO | Competitive Bidding | 2021-10-22 | 2021-11-05 | 2021-11-15 | 2021-11-29 | 2021-11-29 | November 30- December 6, 2021 | December 7- | 2022-02-13 | 2022-02-14 | 2022-02-24 | 2022-03-04 | on-going | on-going | GoP | 5664642.9 | 5664642.9
| 2 units Research Prototype of Greenhouse Type Solar Dryer in Quezon Province |  | NO | Competitive Bidding | [6 empty] | 1st Failure of Bidding | 1st Failure of Bidding (Resolution No. 21-12-58) | 1st Failure of Bidding | 1st Failure of Bidding | 1st Failure of Bidding | N/A | N/A | GoP | 3490648 | 3490648 |  | 1st Failure of Bidding | 1st Failure of Bidding
PHilMech-Goods-21-11-15 | Subscription Renewal of Sophos XGS-43000 Extreme Protection+Email and Web Server Protection For 3 Years | [17 empty] | 9155290.9 | [5 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12
| Subscription Renewal of Sophos XGS-43000 Extreme Protection+Email and Web Server Protection For 3 Years | PMITD | NO | Competitive Bidding | N/A | 2021-11-11 | 2021-11-19 | 2021-12-03 | 2021-12-03 | December 4-10, 2021 | December 11-21, 2021 | 1st Failure of Bidding (Resolution No. 21-12-71) | 1st Failure of Bidding | 1st Failure of Bidding | 1st Failure of Bidding | N/A | N/A | GoP | 1650000 | 1650000 |  | 1st Failure of Bidding | 1st Failure of Bidding
PHilMech Goods 21-11-16 | Supply of Security Services | [17 empty] | 6435792 | [5 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25
| Supply of Security Services | BMTSS | YES | Competitive Bidding | 2021-11-11 | 2021-11-18 | 2021-11-26 | Dec. 27, 2021 | Dec. 15 & 27, 2021 | 2021-12-28 | 2021-12-29 | 2021-12-31 | 01/31/2022 | 2022-02-03 | 2022-02-22 | January- December 2022 | N/A | GoP | 6435792 | 6435792 |  | 5800254.82 | 5800254.82
PHilMech Goods 21-11-17 | Supply of Janitorial Services for the Building and Ground Maintenance | [17 empty] | 2907421.08 | [5 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25
| Supply of Janitorial Services for the Building and Ground Maintenance | AD | YES | Competitive Bidding | 2021-11-11 | 2021-11-18 | 2021-12-01 | 2021-12-15 | 2021-12-15 | December 16-20, 2021 | December 21, 2021 | December 31, 2021 | 2022-02-02 | 2/4/12022 | 2022-02-23 |  |  | GoP | 2907421.08 | 2907421.08 |  | 2461658.78 | 2461658.78
PHilMech-Goods-21-11-18 | Supply and Delivery of Motor Vehicles | [17 empty] | 12600000 | [5 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03
| Supply and Delivery of 6 Units Pickup | AD | YES | Competitive Bidding | 2021-11-23 | 2021-12-02 | 2021-12-10 | 2021-12-23 | 2021-12-23 | December 24, 2021 | December 27, 2021 | December 31, 2021 | 2022-02-04 | 2022-02-14 | 2022-02-22 |  |  | GoP | 12600000 |  | 12600000 | 11472600 |  | 11472600
| Supply and Delivery of Various Office Furniture and Fixtures for the AFMechERN Building | [17 empty] | 4836000
PHilMech Goods 21-11-19 | 52 pcs Laminated partition with glass 2 tones Front Panel (with installation); 120cm (L) x 150cm (H) x 6cm (W) | EDD | NO | Competitive Bidding | 2021-11-17 | 2021-11-24 | 2021-12-03 | 2021-12-16 | 2021-12-16 | 2022-01-18 | January 19- February 14, 2022 | 2022-02-24 | 02/25/2022 | 2022-03-10 | 2022-03-29 | 2022-05-26 | 2022-06-02 | GoP | 2606500 | 2606500 |  | 1180790 | 1180790 |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2021-11-25
117 pcs Laminated partition with glass 2 tones Side Panel (with installation); 100cm (L) x 150cm (H) x 6cm (W)
| 78 pcs Worktop table (with installation) | EDD | NO | [6 empty] | 2022-01-18 | 2022-02-06 | 2022-02-24 | 2022-02-28 | 2022-03-10 | 2022-03-29 | 2022-06-01 | on-going |  | 2229500 | 2229500 |  | 2197776.2 | 2197776.2
5 pcs Executive Desk 1 (assembled)
2 pcs Executive Desk 2 (assembled)
7 pcs Executive Chair
86 pcs Office Chair
2 pcs Executive Table (assembled)
2 pcs High Chair
39 pcs Conference Chair
21 pcs Training Table
40 pcs Stackable Chair
83 pcs Mobile Pedestal
14 pcs Printer Table (assembles)
6 pcs Free Standing Table 1 (assembled)
4 pcs Free Standing Table 2 (assembled)
2 pcs Working table (assembled)
4 pcs Locker Cabinet
16 pcs Vertical Filing Cabinet
24 pcs Lateral Filing Cabinet
6 pcs Multi-purpose Storage Rack (assembled)
| 3 sets Table Set | [31 empty] | 22627584 | 22627584
7 pcs Modular Conference Table
| Supply, Delivery and Installation of Air Conditioning Units for ICT-ERN Building | [17 empty] | 3911000 |  | 3911000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03
PHilMech Goods 21-11-20 | Supply, Delivery and Installation of Air Conditioning Units for ICT-ERN Building | PMITD | YES | Competitive Bidding | 2021-11-22 | 2021-12-02 | 2021-12-10 | 2021-12-23 | 2021-12-23 | N/A | N/A | N/A | 1st Failure of Bidding | 1st Failure of Bidding | 1st Failure of Bidding | N/A | N/A | GoP | 3911000 |  | 3911000 | N/A |  | N/A
| Supply, Delivery, Installation, Configuration and Commissioning/Testing of Additional Hyperconverged Infra Server Node and Upgrade of HCI Server | [17 empty] | 7600000 |  | 7600000 | 7600000 |  | 7600000 | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03
PHilMech Goods 21-11-21 | Supply, Delivery, Installation, Configuration and Commissioning/Testing of Additional Hyperconverged Infra Server Node and Upgrade of HCI Server | PMITD | YES | Competitive Bidding | 2021-11-23 | 2021-12-02 | 2021-12-10 | 2021-12-24 | 2021-12-24 | December 27, 2021 | December 28, 2021 | December 31 ,2021 | 2022-02-02 | 2022-02-12 | 2022-03-04 | on-going | on-going | GoP | 7600000 |  | 7600000 | 7600000 |  | 7600000
| Rebidding for the Supply of Labor and Materials for the Fabrication, On-site Delivery, Installation and Testing of Research Prototype of Greenhouse Type Solar Dryer in Quezon | [17 empty] | 4082686.44 | 4082686.44 |  |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14
PHilMech Goods 21-11-22 | Rebidding for the Supply of Labor and Materials for the Fabrication, On-site Delivery, Installation and Testing of Research Prototype of Greenhouse Type Solar Dryer in Quezon | AMD | NO | Competitive Bidding | N/A | 2021-12-14 | 2021-12-21 | 2022-01-11 | 2022-01-11 | N/A | N/A | Cancelled/ Terminated Bidding Project | N/A | N/A | N/A | N/A | N/A | GoP | 4082686.44 | 4082686.44 |  | N/A | N/A
PHilMech-Goods-22-03-06 | Rebidding for the Subscription Renewal of Sophos XGS-4300 Extreme Protection+Email and Web Server Protection for 3 Years | PMITD | NO | Competitive Bidding | N/A | 2022-04-05 | 2022-04-13 | 2022-04-26 | 2022-04-26 | April 27- May 2, 2022 | May 3-5, 2022 | 2022-05-13 | 2022-05-13 | 2022-05-17 | 2022-05-19 | 2022-06-21 | 2022-06-29 | GoP | 1650000 | 1650000 |  | 1584000 | 1584000 |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-04-07
| Rebidding for the Subscription Renewal of Sophos XGS-4300 Extreme Protection+Email and Web Server Protection for 3 Years | [17 empty] | 1650000 | 1650000 |  | 1584000 | 1584000
Total Alloted Budget of Procurement Activities | [18 empty] | 1754879681.98
Total Contract Price of Procurement Activites Conducted | [18 empty] | 434216929.8
Total Savings (Total Alloted Budget - Total Contract Price) | [18 empty] | 1320662752.18
ON-GOING PROCUREMENT ACTIVITIES
RFQ No.R-22-02-100 | Supply, Delivery and Testing of Mechanical Rice Threshers: Axial Flow | [17 empty] | 19110000
| Rebidding for the Supply, Delivery and Testing of 11 Units 0.8-1.2 ton/hr Axial-Flow Threshers for Regions XI & XII | FMFOD | NO | NP-53.1 Two Failed Biddings | N/A | 2022-02-24 | N/A | 2022-03-04 | 2022-03-04 | March 5-11, 2022 | March 12- April 7, 2022 | Declared by the HOPE as Failed Bidding | N/A | N/A | N/A | N/A | N/A |  | 1876875 |  | Declared by the HOPE as Failed Bidding
| Rebidding for the Supply, Delivery and Testing of 101 Units 0.8-1.2 ton/hr Snap on/ Detachable Axial-Flow Threshers for Regions IX, X & BARMM | FMFOD | NO | NP-53.1 Two Failed Biddings | N/A | 2022-02-24 | N/A | 2022-03-04 | 2022-03-04 | March 5-11, 2022 | March 12- April 7, 2022 | Declared by the HOPE as Failed Bidding | N/A | N/A | N/A | N/A | N/A |  | 17233125 |  | Declared by the HOPE as Failed Bidding
| Supply, Delivery and Testing of Walking-Type Agricultural Tractors | [17 empty] | 2057580 |  | 0
| Supply and Delivery and Testing of 12 units Walking-Type Agricultural Tractors with Complete Accessories (For Island Provinces) for Region II | FMFOD | NO | NP-53.1 Two Failed Biddings | N/A | 2022-02-24 | N/A | 2022-03-04 | 2022-03-04 | N/A | N/A | 1st Failure of Negotiated Procurement per BAC Reso 22-04-29 | N/A | N/A | N/A | N/A | N/A |  | 2057580 |  | 1st Failure of Negotiated Procurement per BAC Reso 22-04-29
PHilMech-RCEF-22-04-02 | Supply, Delivery, Installation andTesting of Multi-Stage Rice Mill | [17 empty] | 97200000 |  | 97200000
| Supply, Delivery, Installation and Testing of 2 units Multi-Stage Rice Mill for Isabela and Bukidnon | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | 2022-05-18 | 2022-05-18 | May 18-24, 2022 | May 25- June 16, 2022 | 06/21/2022 | 06/22/2022 | 6/27/2022 | 06/29/2022 | on-going | on-going | Special Purpose Fund | 97200000 |  | 97200000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-04-27 | 2022-04-27 | 2022-04-27 | 2022-04-27 | 2022-04-27
PHilMech-RCEF-22-04-04 | Supply, Delivery, Installation andTesting of Various Heated Air Mechanical Dryers | [17 empty] | 964245752 |  | 964245752
| Supply, Delivery, Installation and Testing of 6 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region II | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A | Cancelled/ Terminated Bidding Project | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 18600000 |  | 18600000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-04-27 | 2022-04-27 | 2022-04-27 | 2022-04-27 | 2022-04-27
| Supply, Delivery, Installation and Testing of 5 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region III | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 15500000 |  | 15500000
| Supply, Delivery, Installation and Testing of 5 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region IV-B | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 15500000 |  | 15500000
| Supply, Delivery, Installation and Testing of 5 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region VI | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 15500000 |  | 15500000
| Supply, Delivery, Installation and Testing of 2 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region VII | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 6200000 |  | 6200000
| Supply, Delivery, Installation and Testing of 12 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Corrosive Environment) with Petroleum Based Fuel Heating System for Region VIII | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 37200000 |  | 37200000
| Supply, Delivery, Installation and Testing of 12 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Regions CAR & II | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 32400000 |  | 32400000
| Supply, Delivery, Installation and Testing of 20 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region I | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 54000000 |  | 54000000
| Supply, Delivery, Installation and Testing of 29 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region III | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 78300000 |  | 78300000
| Supply, Delivery, Installation and Testing of 14 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Regions IV-B and V | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 37800000 |  | 37800000
| Supply, Delivery, Installation and Testing of 6 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Regions VI and VII | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 16200000 |  | 16200000
| Supply, Delivery, Installation and Testing of 17 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region VIII | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 45900000 |  | 45900000
| Supply, Delivery, Installation and Testing of 15 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Petroleum Based Fuel Heating System for Region XI, XII & BARMM | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 40500000 |  | 40500000
| Supply, Delivery, Installation and Testing of 8 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region I | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 25600000 |  | 25600000
| Supply, Delivery, Installation and Testing of 10 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region II | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 32000000 |  | 32000000
| Supply, Delivery, Installation and Testing of 11 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Regions III & IV-A | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 35200000 |  | 35200000
| Supply, Delivery, Installation and Testing of 14 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region VI | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 44800000 |  | 44800000
| Supply, Delivery, Installation and Testing of 11 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Region IX | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 35200000 |  | 35200000
| Supply, Delivery, Installation and Testing of 12 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for Regions X, XI & XII | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 38400000 |  | 38400000
| Supply, Delivery, Installation and Testing of 15 Units Heated Air Mechanical Grain Dryer - Recirculating Batch Type (For Non-Corrosive Environment) with Biomass and Petroleum Based Fuel Heating System for CARAGA Region | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 48000000 |  | 48000000
| Supply, Delivery, Installation and Testing of 4 units Heated Air Mechanical Grain Dryers- Recirculating Batch Type for Isabela and Bukidnon | FMFOD | NO | Competitive Bidding | 2022-04-11 | 2022-04-26 | 2022-05-04 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Special Purpose Fund | 14000000 |  | 14000000
PHilMech-RCEF-22-04-01-Rebidding | Supply, Delivery, Installation andTesting of Various Rice Mills | [17 empty] | 138722876 |  | 138722876 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11
| Supply, Delivery, Installation and Testing of 4 units Single-Pass Rice Mill (Mobile/Trailed Type) for Island Municipalities in Region II | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 9, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 4628700 |  | 4628700
| Supply, Delivery, Installation and Testing of 9 units Single-Pass Rice Mill (Mobile/Trailed Type) for Region I | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 9, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 8032500 |  | 8032500
| Supply, Delivery, Installation and Testing of 7 units Single-Pass Rice Mill (Mobile/Trailed Type) for Region II | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 9, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 6247500 |  | 6247500
| Supply, Delivery, Installation and Testing of 14 units Multi Stage Rice Mill for Regions VII & VIII | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 9, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 72930368 |  | 72930368
| Supply, Delivery, Installation and Testing of 9 units Multi Stage Rice Mill for Regions IX, X, XI & CARAGA | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 9, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 46883808 |  | 46883808
PHilMech-RCEF-22-04-03-Rebidding | Supply, Delivery and Testing of Walking-Type Agricultural Tractors | [17 empty] | 30272052 |  | 30272052 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11
| Supply and Delivery and Testing of 138 units Walking-Type Agricultural Tractors with Complete Accessories for Regions III, IVA & V | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 6, 2022 | June 7-22, 2022 | 2022-07-05 | 2022-07-06 | on-going | on-going | on-going | on-going | Special Purpose Fund | 23764980 |  | 23764980
| Supply and Delivery and Testing of 33 units Walking-Type Agricultural Tractors with Complete Accessories (For Island Provinces) for Regions II, IV-B & V | FMFOD | NO | Competitive Bidding | 2022-04-18 | 2022-05-07 | 2022-05-16 | 2022-05-30 | 2022-05-30 | May 31-June 6, 2022 | June 7-22, 2022 | 2022-07-05 | 2022-07-06 | on-going | on-going | on-going | on-going | Special Purpose Fund | 6507072 |  | 6507072
| Supply, Delivery and Testing of Rice Combine Harvesters | [17 empty] | 748102000 |  | 748102000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-05-27 | 2022-05-27 | 2022-05-27 | 2022-05-27 | 2022-05-27
PHilMech-RCEF-22-05-05 | Supply, Delivery and Testing of 54 units Rice Combine Harvesters for Cluster I (Regions I & III) | FMFOD | NO | Competitive Bidding | 2022-05-05 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 94500000 |  | 94500000
| Supply, Delivery and Testing of 45 units Rice Combine Harvesters for Cluster II (Regions CAR & II) | FMFOD | NO | Competitive Bidding | 2022-05-05 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 78750000 |  | 78750000
| Supply, Delivery and Testing of 49 units Rice Combine Harvesters for Cluster III (Regions IV-A, IV-B & V) | FMFOD | NO | Competitive Bidding | 2022-05-05 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 86946000 |  | 86946000
| Supply, Delivery and Testing of 128 units Rice Combine Harvesters for Cluster IV (Regions VI, VII, VIII) | FMFOD | NO | Competitive Bidding | 2022-05-05 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 230656000 |  | 230656000
| Supply, Delivery and Testing of 106 units Rice Combine Harvesters for Cluster V (Regions IX, X, CARAGA) | FMFOD | NO | Competitive Bidding | 2022-05-05 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 185500000 |  | 185500000
| Supply, Delivery and Testing of 41 units Rice Combine Harvesters for Cluster VI (Regions XI, XII & BARMM) | FMFOD | NO | Competitive Bidding | 2022-05-05 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 71750000 |  | 71750000
| Supply, Delivery and Testing of Rice Reapers | [17 empty] | 76065000 |  | 76065000
PHilMech-RCEF-22-05-06 | Supply, Delivery and Testing of 134 Units Rice Reapers for Luzon A | FMFOD | NO | Competitive Bidding | 2022-05-11 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 22110000 |  | 22110000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-05-27 | 2022-05-27 | 2022-05-27 | 2022-05-27 | 2022-05-27
| Supply, Delivery and Testing of 137 Units Rice Reapers for Luzon B | FMFOD | NO | Competitive Bidding | 2022-05-11 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 22605000 |  | 22605000
| Supply, Delivery and Testing of 87 Units Rice Reapers for Visayas | FMFOD | NO | Competitive Bidding | 2022-05-11 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 14355000 |  | 14355000
| Supply, Delivery and Testing of 103 Units Rice Reapers for Mindanao | FMFOD | NO | Competitive Bidding | 2022-05-11 | 2022-05-26 | 2022-06-03 | 2022-06-17 | 2022-06-17 | June 18-23, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 16995000 |  | 16995000
| Rebidding for the Subscription Renewal of Sophos XGS-4300 Extreme Protection+Email and Web Server Protection for 3 Years | [23 empty] | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20
PHilMech Good 22-02-01 | Rebidding for the Subscription Renewal of Sophos XGS-4300 Extreme Protection+Email and Web Server Protection for 3 Years | PMITD | NO | Competitive Bidding | N/A | 2022-01-18 | 2022-01-26 | 2022-02-09 | 2022-02-09 | February 10-11, 2022 | February 12-March 1, 2022 | Cancelled/ Terminated Bidding Project | N/A | N/A | N/A | N/A | N/A | GoP | 1650000 |  | 1650000 | Cancelled/ Terminated Bidding Project |  | Cancelled/ Terminated Bidding Project
PHilMech Goods 22-04-02 | Supply and Delivery of Various I.T. Related Supplies and Equipment | PMITD | NO | Competitive Bidding | 4/6/2022 & 4/8/2022 | 2022-04-13 | 2022-04-22 | 2022-05-06 | 2022-05-06 | May 7-13, 2022 | May 14-17, 2022 | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-06-06 | on-going | on-going | GoP | 3644323 | 3644323 |  | 3355330 | 3355330 |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-04-13 | 2022-04-13 | 2022-04-13 | 2022-04-13 | 2022-04-13
| 37 units Desktop Computer with complete accessories 14 units Monitor 14 units Laptop 50 units Solid State Drive 500GB 50 units ATX Power Supply, 650 watts 10 units Hard Disk Drive 4TB, SATA 6 Gb/s, 38 units Keyboard and Mouse Combo 50 pc Wireless Mouse 12 units Web Camera 3 units Desktop Speaker 11 units UPS Unit for Desktop | [17 empty] | 1656323 | 1656323 |  | 1631710 | 1631710
| 34 units Portable Drive 51 units USB Flash Drive, all-metal, 2-in-1, USB Type-C and Type A, 128GB Capacity 2000 units USB Flash Drive, 16GB/32GB, USB 3.0 | [8 empty] | May 7-13, 2022 | May 14-17, 2022 | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-06-06 | on-going | on-going | GoP | 1184500 | 1184500 |  | 993670 | 993670
| 19 units Portable Document Scanner | [8 empty] | May 7-13, 2022 | May 14-17, 2022 | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-06-06 | on-going | on-going | GoP | 275500 | 275500 |  | 270750 | 270750
| 44 units Multi-Function Printer | [8 empty] | May 7-13, 2022 | May 14-20, 2022 | 2022-05-25 | 2022-05-25 | 2022-06-03 | 2022-06-10 | on-going | on-going | GoP | 528000 | 528000 |  | 459200 | 459200
PHilMech Goods 22-02-03 | Rebidding for the Supply, Delivery and Installation of Air Conditioning Units for ICT-ERN Building | EDD | NO | Competitive Bidding | N/A | 2022-02-08 | 2022-02-16 | 2022-03-02 | 2022-03-02 | N/A | N/A | 2nd Failure of Bidding | N/A | N/A | N/A | N/A | N/A | GoP | 3911000 |  | 3911000 |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-02-11 | 2022-02-11 | 2022-02-11 | 2022-02-11 | 2022-02-11
| 14 units 1.0 hp Inverter Split Type wall mounted 30 units 1.5 hp Inverter Split Type wall mounted 2 units 2.0 hp Inverter Split Type wall mounted 3 units 2.5 - 2.6 hp Inverter Split Type wall mounted 3 units 2.9 - 3.0 hp Inverter Split Type wall mounted at server room 6 units 4.0 hp/3 TR Inverter Split Type Floor standing Installation of air conditioning units | [17 empty] | 3911000 |  | 3911000
PHilMech-Goods-22-03-04 | Rebidding for the Supply of Labor and Materials for the Fabrication, On-site Delivery, Installation and Testing of 2 Units Research Prototype of Greenhouse Type Solar Dryers in Quezon | AMD | NO | Competitive Bidding | N/A | 2022-03-02 | 2022-03-18 | 2022-03-31 | 2022-03-31 | N/A | N/A | 2nd Failure of Bidding | N/A | N/A | N/A | N/A | N/A | GoP | 4082686.44 | 4082686.44 |  |  |  |  | COA, Nueva Ecija Seed Growers Association, Bantug PMC, San Jose City Chamber of Commerce and Industry, PSABE-Central Luzon Chapter | 2022-03-04 | 2022-03-04 | 2022-03-04 | 2022-03-04 | 2022-03-04
| Rebidding for the Supply of Labor and Materials for the Fabrication, On-site Delivery, Installation and Testing of 2 Units Research Prototype of Greenhouse Type Solar Dryers in Quezon | [17 empty] | 4082686.44 | 4082686.44
PHilMech Goods 22-06-07 | Supply and Delivery of THHN Electrical Copper Wire | [17 empty] | 1200000 | 1200000 |  |  |  |  | COA, San Jose City Chamber of Commerce and Industry, Philippine Constructors Association, Inc. | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
| Supply and Delivery of 3 Rolls THHN Electrical Copper Wire | AD | NO | Competitive Bidding | N/A | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-06-30 | July 1-4, 2022 | on-going | on-going | on-going | on-going | on-going | on-going | on-going | GoP | 1200000 | 1200000
RFQ No. 22-03-250 | Supply, Delivery, Installation and Testing of Air Conditioning Units for ICT-ERN Building | AD | NO | NP-53.1 Two Failed Biddings | N/A | 2022-03-21 | N/A | 2022-03-25 | 2022-03-25 | March 26- April 1, 2022 | April 2-18, 2022 | 04/29/2022 | 2022-05-06 | 2022-05-11 | 2022-05-17 | on-going | on-going | GoP | 3911000 |  | 3911000 | 3838946 |  | 3838946 | N/A | N/A | N/A | N/A | N/A | N/A
RFQ No. 22-04-307 | Supply of Labor and Materials for the Fabrication, On-site Delivery, Installation and Testing of Research Prototype of Greenhouse Type Solar Dryer in Quezon | AMD | NO | NP-53.1 Two Failed Biddings | N/A | 2022-04-06 | N/A | 2022-04-11 | 2022-04-11 | April 12-18, 2022 | April 19-May 4, 2022 | 2022-05-12 | 2022-05-13 | 2022-05-17 | 2022-05-23 | on-going | on-going | GoP | 4082686.44 | 4082686.44 |  | 3848925.3 | 3848925.3 |  | N/A | N/A | N/A | N/A | N/A | N/A
RFQ-22-05-264 | School on the Air: Radyo Eskwela “Angat Ani sa Tamang Makinarya” Season 3 | ACD | NO | NP-53.6 Scientific Scholarly, Artistic Work, Exclusive Technology and Media Services | N/A | N/A | N/A | N/A | N/A | on-going | on-going | on-going | on-going | on-going | on-going | on-going | on-going | Special Purpose Fund | 10000000 | 10000000 |  | 9500000 | 9500000 |  | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities
Total Contract Price of Procurement Activites Conducted
Total Savings (Total Alloted Budget - Total Contract Price)
[14 empty] | Total Alloted Budget of On-going Procurement Activities |  |  |  |  | 2098613269.44
|  | Prepared by: | [16 empty] | Recommended for Approval by: | [6 empty] | APPROVED:
|  | RICHELLE ANN L. MOROTA | [16 empty] | RONALDO SEBASTIAN R. REYES | [6 empty] | DIONISIO G. ALVINDIA, PhD.
|  | BAC Secretariat | [16 empty] | BAC Chairperson | [6 empty] | Head of the Procuring Entity

## LCB (hidden)
Code (UACS/PAP) | Lot No. | Procurement Program/Project |  |  | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [13 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  | Winning Bidder | No. of Machineries |  |  | Pre-Proc Conference | Ads/Post of IB | Invitation to Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Notice of Receipt of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
|  | Supply, Delivery and Testing of Four-Wheel Tractors | [19 empty] | 465894690 |  | 465894690 | 156700000 |  | 156700000
| 13 | Supply, Delivery and Testing of 118 Units Four-Wheel Tractors for Regions VII & VIII | AIMS Agri Ventures, Inc. | 118 |  |  | Notice of Post-DQ (Aug. 12, 2021) | Motion for Reconsideration (Aug.13, 2021) | Answer to MR (Aug. 20, 2021) | [11 empty] | GOP- RCEF FY 2021 | 153400000 |  | 153400000 | [11 empty] | 153223000 | 153223000
|  | Supply, Delivery and Testing of Rice Combine Harvesters | [19 empty] | 156247345 |  | 156247345 | 78350000 |  | 78350000
| 10 | Supply, Delivery and Testing of 41 Units Rice 65-85HP Combine Harvesters for Visayas (Regions VI, VII & VIII) | Agricomponent Corporation | 41 |  |  | Notice of Post-DQ (Aug. 12, 2021) | Motion for Reconsideration (Aug.14, 2021) | Answer to MR (Aug. 18, 2021) | [11 empty] | GOP- RCEF FY 2020 | 77614845 |  | 77614845 | [11 empty] | 77614345 | 77614345
|  | Supply, Delivery and Testing of Rice Reapers | [19 empty] | 39316250 |  | 39316250 | 39175000 |  | 39175000
| 2 | Supply, Delivery and Testing of 156 Units Rice Reapers for Visayas (Regions VI,VII & VIII) | D’ Brothers International Trading Corporation | 156 |  |  | Notice of Post-DQ (Aug. 13, 2021) | [14 empty] | 24533340 |  | 24533340 | 24445200 |  | 24445200
| 3 | Supply, Delivery and Testing of 94 Units Rice Reapers for Mindanao (Regions IX, X, XI, XII & BARMM) | D’ Brothers International Trading Corporation | 94 |  |  | Notice of Post-DQ (Aug. 13, 2021) | [14 empty] | 14782910 |  | 14782910 | 14729800 |  | 14729800

## Computation of Total (hidden)
Lot
Seeder | 1 | 16780000
Waliking-Type | 5 | 114070000
Floating Tiller | 5 | 48074040
Axial-Flow Threshers | 3 | 27055256 | 9437880
1730278
15887098
Rice Mill w/ Impeller Huller | 2 | 18600000
| 16 | 224579296
Total ABC |  |  |  | 5196828896
Supply, Delivery and Testing of Rice Precision Seeders |  |  |  | 16780000
Supply, Delivery and Testing of Walking-Type Agricultural Tractors |  |  |  | 114070000
Supply, Delivery and Testing of Axial-Flow Threshers |  |  | Lot 1 | 9437880
|  |  | Lot 3 | 1730278
|  |  | Lot 5 | 15887098
Supply, Delivery, Installation, Testing and Commissioning of Rice Mill with Impeller Huller |  |  |  | 18600000
176505256
5020323640

## Sheet1 (hidden)
Competitive Bidding
Limited Source Bidding
Direct Contracting
Repeat Order
Shopping
NP-53.1 Two Failed Biddings
NP-53.2 Emergency Cases
NP-53.3 Take-Over Contract
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation, NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement

## Sheet2
| Rebidding for the Supply and Delivery of Various I.T. Equipment (CO 2021) |  |  |  | 238311680000000 |  | 238311680000000 | 0 |  | 0
| Negotiated Procurement for the Supply and Delivery of Various I.T. Equipment (CO 2021) |  |  |  | 98483712000000 |  | 0 | 0 |  | 0
| Supply and Delivery of Various Office Supplies for the First Quarter 2021 |  |  |  | 49241856000000 | 0
| Supply and Delivery of Various I.T. and Other Related Supplies for the First Quarter 2021 |  |  |  | 49241856000000 | 0
| Rebidding for the Supply and Delivery of Various Office Supplies for the First Quarter 2021 |  |  |  | 20672128000000 | 0
| Rebidding for the Supply and Delivery of Various I.T. and Other Related Supplies for the First Quarter 2021 |  |  |  | 20672128000000 | 0
| Supply and Delivery of Various Office Supplies for the 3rd Quarter of 2021 |  |  |  | 7897600000000 | 0
| Supply and Delivery of Various I.T. Equipment and Other Related Supplies for the 3rd Quarter of 2021 |  |  |  | 7897600000000 | 0
| Rebidding for the Supply and Delivery of Various Office Supplies for the 3rd Quarter of 2021 |  |  |  | 4876928000000 | 0
| Rebidding for the Supply and Delivery of Various I.T. Equipment and Other Related Supplies for the 3rd Quarter of 2021 |  |  |  | 3020672000000 | 0
| Supply and Delivery of Various Office Supplies for the 4th Quarter of 2021 |  |  |  | 1856256000000 | 0 |  | 0 | 0
| Supply and Delivery of Various I.T. Equipment and Other Related Supplies for the 4th Quarter of 2021 |  |  |  | 1164416000000 | 0
| Rebidding for the Supply and Delivery of Various I.T. Equipment and Other Related Supplies for the 4th Quarter of 2021 |  |  |  | 691840000000 | 0
| Supply, Delivery and Testing of Four-Wheel Tractors |  |  |  | 472576000000 |  | 0 | 5208000000 |  | 0
| Supply, Delivery and Testing of PTO Driven Disc Plow/Harrow Implement for Four-Wheel Tractor |  |  |  | 219264000000 |  | 0 | 2387000000 |  | 0
| Supply, Delivery and Testing of Rice Combine Harvesters |  |  |  | 126720000000 |  | 0 | 1426000000 |  | 0
| Supply, Delivery and Testing of Mechanical Rice Transplanters |  |  |  | 63360000000 |  | 0 | 713000000 |  | 0
| Supply, Delivery and Testing of Rice Precision Seeders |  |  |  | 29184000000 |  | 0 | 248000000 |  | 0
| Supply, Delivery and Testing of Rice Reapers |  |  |  | 15616000000 |  | 0 | 124000000 |  | 0
| Supply, Delivery and Testing of Walking-Type Agricultural Tractors |  |  |  | 8960000000 |  | 0
| Supply, Delivery and Testing of Axial-Flow Threshers |  |  |  | 4608000000 |  | 0 | 124000000 |  | 0
| Supply, Delivery, Installation, Testing and Commissioning of Rice Mill with Impeller Huller |  |  |  | 2048000000 |  | 0
| Supply and Delivery of Various Advocacy Collaterals |  |  |  | 1280000000 | 0 |  | 62000000 | 0
| Supply and Delivery of Various Publications |  |  |  | 768000000 | 0 |  | 62000000 | 0
| Rebidding for the Supply, Delivery and Testing of Rice Precision Seeders |  |  |  | 256000000 |  | 0 | 0 |  | 0
| Rebidding for the Supply, Delivery and Testing of Axial-Flow Threshers |  |  |  | 256000000 |  | 0
| Rebidding for the Supply, Delivery, Installation, Testing and Commissioning of Rice Mill with Impeller Huller |  |  |  | 128000000 |  | 0 | 31000000 |  | 0
REBIDDING FOR THE SUPPLY AND DELIVERY OF VARIOUS PUBLICATIONS
| Rebidding for the Supply and Delivery and Testing of Walking-Type Agricultural Tractors |  |  |  | 128000000 |  | 0 | 31000000 |  | 0
| Supply, Delivery, Installation, Testing and Commissioning of Various Rice Mills |  |  |  | 64000000 |  | 0 | 15500000 |  | 0
| Supply, Delivery and Testing of De-Stoners |  |  |  | 32000000 |  | 0 | 0 |  | 0
| Supply, Delivery, Installation, Testing and Commissioning of Various Heated Air Mechanical Dryers |  |  |  | 16000000 |  | 0
RFQ No. R-21-08-523 | TV Show on Agriculture | ACD | NO | NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 6000000 | 6000000 |  | 6000000 | 6000000
RFQ No. R-21-08-522 | School on the Air | ACD | NO | NP-53.6 Scientific Scholarly, Artistic Work, Exclusive Technology and Media Services | 10000000 | 10000000 |  | 9500000 | 9500000